## README
| README notes | 2017-01-26
Score
ID | WBS | Risk Description | Potential Impact | L | I | L×I | S2 | S3 | Mitigation | Comment
45 | 1.2 | Technical, cost and schedule risks are described in this column. Likelihood is rated from 1 to 5 (with 5 most likely) in the column "Risk Score->L". | Potential impact is desribed here, and rated from 1 to 5 (with 5 most severe) in the column "Risk Score->I". | 2 | 4 | 8 |  |  | If the risk happens, what can be done in response, if anything? | The column Risk Score->LxI contains the multiplication of L and I. Scores from 1 to 5 get a green background, 6 to 12 yellow, 13 to 25 red.
46 | 1.1 | This risk is unlikely. | The impact is minor. | 2 | 2 | 4 |  |  |  | Green.
47 | 1.13 | This risk is moderately likely. | The impact is most severe. | 3 | 5 | 15 |  |  |  | Red.
48 | 1.09.1.2
In addition to the LxI column, there are two additional scores computed from L and I:
S2 is just SQRT(L*I); it gives a more linear scale
S3 is SQRT((L-1)^2+(I-1)^2)+1; this score will emphasize items of high risk or high impact
There is a hidden column J, computing the WBS level 2 value from column A. This is used for sorting.
There is a filter on the sheet. See the little arrows in row 3. This should let you filter for high risks, sort on risk, etc.

## Risks
|  | 2017-02-28 | [12 empty] | 5
|  |  |  | Risk Score | [10 empty] | Total Risk ($*I/5)
WBS | ID | Risk Description | Potential Impact | L | I | L×I | S2 | S3 | Mitigation | Comment | WBS2 | Cost Impact | Schedule Impact | When can risk be retired? | 9419000
1.1 | 1 | Loss of key personnel | somewhat likely, and high impact | 2 | 3 | 6 | 2.4495 | 3.2361 | identify possible replacements, encourage commitment to project and high morale | already has happened, so likely | 1 | 100000 | 3-6 month delay or more depending on personnel lost | At project completion | 40000
1.1 | 2 | Missing Key Milestone leads to funding delays or increased scrutiny | very possible, delays to schedule, possible funding delays recovering from problems. | 3 | 4 | 12 | 3.4641 | 4.6056 | Careful focus on meeting go/no-go milestones |  | 1 | 50000 | several months | After fractional arc test (second go/no-go decision) | 30000
1.1 | 3 | Lack of qualified personnel leads to slow down in overall project schedule | highly likely, schedule slips leading to additional costs | 5 | 2 | 10 | 3.1623 | 5.1231 | diversify suppliers / shops / technicians / etc. |  | 1 | 200000 | 6 months | At project completion | 200000
1.1 | 4 | Insufficient human resource availaibility, especially engineers and technicians, due to conflict with other activities, eg CHESS-U at Cornell, or RHIC operations at BNL. | Schedule overruns, and standing army knock-on effects. | 3 | 3 | 9 | 3 | 3.8284 | Identify the most critical deficiencies as soon as possible, especially with regard to magnet design protoyping and procurement (hybrid and conventional). Develop a Resource Loaded Schedule that includes (at a high level) conflicts with other projects. Increase the relative priority of C-Beta relative to other BNL and CLASSE activities. Hire additional personnel. | The 4 mitigation strategies can be very effective. Two of them would require support from laboratory management. | 1 | 100000 | 3-6 months delay or more | At project completion | 60000
1.1 | 5 | Funding Delays or Cuts from NYSERDA | Fund not available for project to move forward | 1 | 5 | 5 | 2.2361 | 5 | Unless other funding sources are identified, there may be no way for the project to proceed. |  | 1 | 200000 | 12-18 months | At project completion | 40000
1.1 | 6 | Cost estimate (Feb 2017) includes only 2% contingency | Can't complete the project with the available funding | 4 | 5 | 20 | 4.4721 | 6 | Identify additional funding sources. Reduce scope. Scrutinise plans for value engineering opportunbities. |  |  |  |  | At project completion | 0
1.1 | 7 | Schedule is very aggressive. | Can't complete the project on time. | 3 | 4 | 12 | 3.4641 | 4.6056 | Careful planning. |  |  | 2000000 | 12 months | At project completion | 1200000
1.2 | 1 | Random field errors above levels specified in lattice requirements | Beam cannot be steered acceptably for operation with existing correctors. | 2 | 4 | 8 | 2.8284 | 4.1623 | Re-engineering of magnets. Re-design correctors with increased strength. Or run temporarily with worse emittance. | Additional power supplies or BPM electronics | 2 | 300000 | 12 months | After 4-turn test | 120000
1.2 | 2 | Magnetisation of blocks systematically lower or higher than specified range | Forced to lower or higher energy | 2 | 2 | 4 | 2 | 2.4142 | Lower or higher linac energy by a few percent. |  | 2 |  |  |  | 0
1.2 | 3 | Systematic difference in fields, from crosstalk or single-magnet effects, small impact | Orbit differences below 1 mm, dynamically unimportant changes in tune range | 2 | 1 | 2 | 1.4142 | 2 | Tweak linac energy to adjust tune and orbit range if desired, but probably just ignore. |  | 2 | 10000 | 2 weeks | After 4-turn test | 4000
1.2 | 4 | Systematic difference in fields, from crosstalk or single-magnet effects, resulting in larger orbit differences | Orbit differences above 1 mm, dynamically unimportant changes in tune range | 1 | 2 | 2 | 1.4142 | 2 | Systematically offset arc and transition magnets.Tweak linac energy. | Have provision for 2 mm of magnet shift, which should handle several mm of orbit offsets. | 2 | 10000 | 2 weeks | After 4-turn test | 2000
1.2 | 5 | Systematic difference in fields, from crosstalk or single-magnet effects, resulting in unacceptably large tune | Operating tune range will not allow a factor of 4 in energy | 1 | 3 | 3 | 1.7321 | 3 | Adjust linac energy to allow factor of 4 in energy. Systematic quadrupole offset. Downgrade one quadrupole class with shunts to adjust tune range. | Have provision for 2 mm of magnet shift, can pull beam out of region where systematic effects are significant. | 2 | 10000 | 2 weeks | After 4-turn test | 2000
1.2 | 6 | Non-uniformity of correctors or coupling of correctors to each other leads to different correction response than expected. | Correction algorithm not as effective as expected. Design corrector strength not as effective as expected. | 2 | 3 | 6 | 2.4495 | 3.2361 | Rewrite correction algorithm. Minor re-design of correctors. | Could better evaluate likelihood and impact with simulation, but complex. Additional power supplies or BPM electronics. | 2 | 300000 | 12 months | After 4-turn test | 120000
1.2 | 7 | Corrector strengths unexpectedly low. | Beam cannot be steered acceptably for operation with existing correctors. | 1 | 4 | 4 | 2 | 4 | Re-design correctors with increased strength. | Replace power supplies with higher current capability | 2 | 600000 | 12 months | After 4-turn test | 120000
1.2 | 8 | Current ripple leads to excess emittance growth. | Beam loss impairs energy recovery. Radiation beyond permitted bounds. | 2 | 4 | 8 | 2.8284 | 4.1623 | Replace power supplies. Add filtering circuitry. Improve response of corrector systems. | Provide external filtering for power supplies | 2 | 300000 | 12 months | After 4-turn test | 120000
1.3 | 1 | gun failure / insulator punchthough / problem with HVPS | Months and months (6 months) | 2 | 4 | 8 | 2.8284 | 4.1623 | have backup gun, but BNL has backup HVPS in RHIC, Have a 2mA 500KV Glassman PS |  | 3 | 2000000 | 12 months | At project completion | 800000
1.3 | 2 | Buncher IOT Tube | a week to fix, | 2 | 2 | 4 | 2 | 2.4142 | $$$ to repair |  | 3 | 100000 | 1 month | At project completion | 40000
1.3 | 3 | Vacuum / diagnostic failure | fairly likely, but minor impact | 2 | 2 | 4 | 2 | 2.4142 |  |  | 3 | 10000 | 1 month | At project completion | 4000
1.3 | 4 | Cathode preparation issues (FE problems recently) | many minor delays | 4 | 1 | 4 | 2 | 4 | Multiple cathode growth systems / more trained experts in cathode growth. Better growth system diagnostics and testing. |  | 3 | 20000 | 2 months | At project completion | 16000
1.4 | 1 | Main Linac Cryomodule acquires an internal problem, such as a vacuum leak, that requires extensive dismantling, repair and reconstruction. | The MLC would take many months to repair, and would absorb a significant amount of labor. | 2 | 4 | 8 | 2.8284 | 4.1623 | Almost none, except for prevention: exercising great care during the relocation and beam-testing required for go/no-go milestone 1. | The MLC is a complex cryogenic with high power RF and high-vacuum sub-systems. It has mostly been tested, although not yet at full power, nor with beam. | 4 | 500000 | 12 months or more | At project completion | 200000
1.4 | 2 | Internal MLC helium leak (large from welded or inaccessible joint) | Unable to operate MLC at all. Repairs would require signifcant time and labor to recover. | 2 | 5 | 10 | 3.1623 | 5.1231 | Almost none. Cryogenic system is designed to self protect form overpressure events with relief valve and burst disks. Limit thermal cycling between 4K and rom temperature. | The MLC is a complex cryogenic system with high power RF and high-vacuum sub-systems. It has mostly been tested, although not yet at full power, nor with beam. |  | 500000 | 12 months or more | At project completion | 200000
1.4 | 3 | Internal MLC helium leak (large from accessible "threaded"-union/joint) | Unable to operate MLC at all. Installed pumping is not able to keep up with leak rate. Unable to collect liquid helium where it is needed. Repairs would require warming to room temperature but can be done in place. | 2 | 1 | 2 | 1.4142 | 2 | Follow assembly procedures and use experienced staff for installation and assembly. Thorough leak checking during assembly. When relocating MLC special attention should be paid to preventing sudden impacts and/or jarring the cryomodule. |  |  | 100000 | 6 months or more | At project completion | 40000
1.4 | 4 | Internal MLC helium leak inaccessible (small) | MLC can be operated with a small helium leak in which the leak rate does not exceed the pumping speed of installed pumps. | 4 | 1 | 4 | 2 | 4 | Follow assembly procedures and use experienced staff for installation and assembly. Thorough leak checking during assembly. When relocating MLC special attention should be paid to preventing sudden impacts and/or jarring the cryomodule.Be sure to have spare pumps on hand. |  |  | 50000 | 3 months or more | At project completion | 40000
1.4 | 5 | Internal MLC helium leak accessible (small) | MLC can be operated with a small helium leak in which the leak rate does not exceed the pumping speed of installed pumps. | 4 | 1 | 4 | 2 | 4 | Follow assembly procedures and use experienced staff for installation and assembly. Thorough leak checking during assembly. When relocating MLC special attention should be paid to preventing sudden impacts and/or jarring the cryomodule.Be sure to have spare pumps on hand. | Repair if schedule permits. |  | 50000 | 3 months or more | At project completion | 40000
1.4 | 6 | Injector Cryomodule (ICM) acquires an internal problem, such as a vacuum leak, that requires extensive dismantling, repair and reconstruction. | The ICM would take many months to repair, and would absorb a significant amount of labor. | 2 | 5 | 10 | 3.1623 | 5.1231 | Almost none. Cryogenic system is designed to self protect form overpressure events with relief valve and burst disks. Limit thermal cycling between 4K and rom temperature. The internal vacuum systems are not easily repared | Same as the MLC |  | 500000 | 12 months or more | At project completion | 200000
1.4 | 7 | Problem during warm up of MLC to room temperature. | deformation, leak, etc., | 1 | 4 | 4 | 2 | 4 | Follow procedure carefully. Use slow warmup. Monitor expansion rate. | Cavities can be deformed . Cavities can be plastically deformed if tuner are not positioned properly. Deformed MLC cavities would be unusable. |  | 15000000 | Project completion not possible without building new MLC | At project completion
1.4 | 8 | Problem during the moving MLC into final location. | Vacuum leak | 1 | 2 | 2 | 1.4142 | 2 | Don’t drop it. | Don’t drop it. |  | 500000 | 12 months or more | After MLC test | 100000
1.4 | 9 | Problem during the connection of MLC and meam lines. | Contaminants into cavities, Q degradation, field emission, radiation. | 3 | 5 | 15 | 3.873 | 5.4721 | Follow assembly procedures and use experienced staff for installation and assembly. Thorough leak checking during assembly. When relocating MLC special attention should be paid to preventing sudden impacts and/or jarring the cryomodule.Be sure to have spare pumps on hand. |  |  | 100000 | 6 months or more | After MLC test | 60000
1.4 | 10 | Develop a problem during cool down MLC when at final location. | Deformation, leak, etc., | 2 | 2 | 4 | 2 | 2.4142 | Follow controlled slow cooldown procedures, careful monitoring of temperture, vacuum, shrinkage rate. |  |  | 500000 | 12 months or more | After MLC test | 200000
1.4 | 11 | The problem during new SSAs installation and performance test. | stability | 1 | 1 | 1 | 1 | 1 | Technology is well understood | Cornell has experience with proposed vendor. |  |  |  | After fraction arc test | 0
1.4 | 12 | When the MLC sees the first beam. | Beam hits cavity wall a quench and field emission can arise. | 5 | 1 | 5 | 2.2361 | 5 | Careful monitoring and interlocks. | with low beam current lasting damage to cavities is unlikley. |  | 100000 | 3-6 months | After MLC test | 100000
1.4 | 13 | High current beam operation (>10 mA) | HOM issue. | 1 | 5 | 5 | 2.2361 | 5 | Almost none. These comonents cannot be removed without complete MLC diassembly. | HOM absorbers not fully tested yet with beam. Not an issue at low current. |  |  |  |  | 0
1.4 | 14 | RF field and microphonics stability. | Stability of the MLC perfomance | 5 | 2 | 10 | 3.1623 | 5.1231 | Having enough RF power overhead is needed to minimize unstable RF field. | Without energy recovery, assuming 3 kW for micrphonics compensation, and 36 MV energy gain from the MLC, 5 kW amplfiers could support a ~330 uA beam. |  |  |  | ??? | 0
1.5 | 1 | Computer simulations: resonant behaviour not calculated correctly | Lattice needs to be adjusted | 2 | 3 | 6 | 2.4495 | 3.2361 | Computer simulations without periodic boundary conditions |  |  | 250000 | 12 months |  | 100000
1.5 | 2 | Small change in material properties of NdFeB from radiation damage | Excessive beam losses cause drift in magnetic qualtiy field, still within range of correctors | 3 | 2 | 6 | 2.4495 | 3.2361 | Review machine loss control system. Re-run machine correction periodically |  |  | 20000 | 2 months |  | 12000
1.5 | 3 | Large change in material properties of NdFeB from radiation damage | Excessive beam losses make some magnets unusable | 2 | 4 | 8 | 2.8284 | 4.1623 | Review machine loss control system. Replace damaged magnets. | Should see this coming. Halbachs will take 4 to 5 months to fabricate & replace. |  | 200000 | 6 months |  | 80000
1.5 | 4 | Residual non-allowed multipoles in the Halbach magnets | Orbit differences, beam loss depending on magnitude | 2 | 4 | 8 | 2.8284 | 4.1623 | PMM field vector measurement/shimming. Multipole tuning rods. Block sorting. | Revisit magnet design/tolerances after pre-production and/or 1st article fabrication. |  | 50000 | 3 months |  | 20000
1.5 | 5 | Permanent magnet strength from batch sample does not reflect true average | Strength of magnet systematically wrong by a few percent | 1 | 3 | 3 | 1.7321 | 3 | Measure field vector on all blocks, test pre-production and 1st article magnets. | Use quad corrector coil as a last resort |  | 300000 | 12 months |  | 60000
1.5 | 6 | Temperature coefficient permanent magnets larger than expected | Temperature drift of gradient, resulting in orbit differences | 1 | 3 | 3 | 1.7321 | 3 | Better water system stabilization | Use quad corrector coil as a last resort |  | 300000 | 12 months |  | 60000
1.5 | 7 | Temperature coefficient permanent magnets varies within batch | Strength variations aren't the same, small multipoles appear at off-nominal temperature | 1 | 2 | 2 | 1.4142 | 2 | Temperature control during PMM field vector measurement | Better water system stabilization |  | 20000 | 3 months |  | 4000
1.5 | 8 | Geometric block tolerances larger than expected | Unwanted multipoles, gradient variation, leading to orbit differences | 1 | 4 | 4 | 2 | 4 | Drawing tolerances in agreement with vendor capabilities, vendor quality assurance control | Unlikely, good quality blocks were delivered for prototypes, active QA for production |  | 300000 | 12 months |  | 60000
1.5 | 9 | Mechanical properties of magnet holder inadequate | Magnet deformed, systematic multipoles appear | 1 | 3 | 3 | 1.7321 | 3 | Vendor quality assurance control, pre-production measurement and testing | Unlikely, Aluminum frame is stiffer and has been analyzed for stress and deflection |  | 20000 | 2 months |  | 4000
1.5 | 10 | Corrector strength dipole insufficient | Lattice errors higher than expected | 3 | 3 | 9 | 3 | 3.8284 | Lattice studies continue, increase power supply current, increase dipole coil turns | Corrector coils can be driven at higher currents; more turns added after pre-production tests |  | 300000 | 12 months | After 4-turn test | 180000
1.5 | 11 | Too much magnet-to-magnet gradient variation (>0.2%) | Poor optics performance | 2 | 2 | 4 | 2 | 2.4142 | Power the quadrupole correctors |  |  | 300000 | 12 months | After one-turn test | 120000
1.5 | 12 | Dipole correctors influence Halbach gradient quality negatively | Orbit differences, may limit ability to correct for fied errors | 1 | 3 | 3 | 1.7321 | 3 | Re-design dipole corrector winding configuration to reduce multipoles | Unlikely, beam position is in small diameter central field region of a large corrector |  |  | ? | After one-turn test | 0
1.5 | 13 | Magnet assembly takes longer than anticipated | Impact schedule and cost | 3 | 4 | 12 | 3.4641 | 4.6056 | Pre-production and 1st article magnet lessons learned & tight vendor control | Careful planning, well documented requests for proposal, communication with vendors, resource availability |  | 100000 | 6-9 months | After girder production run complete (Milestome 7) | 60000
1.5 | 14 | Shimming and multipole tuning of magnets takes longer than anticipated | Impact schedule and cost | 2 | 3 | 6 | 2.4495 | 3.2361 | Pre-production and 1st article magnet lessons learned & tight vendor control | Careful planning, resource availability |  | 100000 | 6-9 months | After girder production run complete (Milestome 7) | 40000
1.5 | 15 | Girder integration issues, magnet vendor quality, late delivery, excessive tuning time & protoype girder assembly schedule, production testing, and parts flow choreography. | Schedule impact leading to cost overruns. Vendor cost overruns. | 3 | 3 | 9 | 3 | 3.8284 | Pre-production and 1st article girder lessons learned & tight vendor control | Careful planning, well documented requests for proposal, communication with vendors, resource availability |  | 100000 | 6-9 months | After girder production run complete (Milestome 7) | 60000
1.5 | 16 | Halbach magnets with corrector coils cost more than anticipated | Cost | 4 | 3 | 12 | 3.4641 | 4.6056 | Determine more realistic cost after pre-production magnet fabrication |  |  | 2000000 | 3 months | After receiving production Halbach magnets for one-turn test | 1600000
1.6 | 1 | Physics: Bunch separation and the ability to correct | Moderate impact to the final Four Pass stage of the CBeta project | 3 | 3 | 9 | 3 | 3.8284 | Run at low current? Adjust or add correctors? |  | 6 | 50000 | 6 months | After 4-turn test | 30000
1.6 | 2 | Higher than expected beam loss resulting in increased radiation | Unsafe conditions and tripping radiation interlocks | 3 | 3 | 9 | 3 | 3.8284 | Better alignment(?), Increase shielding, run lower current(?) |  | 6 | 50000 | 6 months | After 4-turn test | 30000
1.6 | 3 | Expandable bellows does not have the needed range for path length adjustment | Cannot obtain the correct path length to operate multi-energy levels | 2 | 3 | 6 | 2.4495 | 3.2361 | Develop additional configuration designs to achieve the correct path length adjustment | Additional configuration changes will add cost and will take the system down (breaking vacuum) to implement | 6 | 100000 | 6 months | After 4-turn test | 40000
1.6 | 4 | Magnet location can not meet the required accuracy | Unable to correct the beam trajectory | 2 | 1 | 2 | 1.4142 | 2 | Redevelop mounting design, add redundant surveying methods | Additional design effort will add cost | 6 | 30000 | 3 months | After 4-turn test | 12000
1.6 | 5 | Cross-talk between magnets affects the beam trajectory in an unpredicted manor | Unable to correct the beam trajectory | 2 | 3 | 6 | 2.4495 | 3.2361 | Shielding? Better controls correction? |  | 6 | 50000 | 6 months | After 4-turn test | 20000
1.6 | 6 | Temperature gradient too high for stable running | Unable to correct the beam trajectory quick enough | 2 | 3 | 6 | 2.4495 | 3.2361 | Better controls correction? Increase local cooling? Increase environmental temperature stability? |  | 6 | 50000 | 3 months | After 4-turn test | 20000
1.6 | 7 | Septum magnet affects low energy beam line | Creates instability in the beam line | 3 | 3 | 9 | 3 | 3.8284 | Shielding? Better controls correction? | May need to move vacuum chamber | 6 | 75000 | 6 months | After 4-turn test | 45000
1.6 | 8 | Septum magnets are more complicated and costly than anticipated | Cost and beam dynamic issues | 4 | 3 | 12 | 3.4641 | 4.6056 | Smart lattice and magnet design |  | 6 | 250000 | 6 months | After septum magnets are designed, fabricated and measured | 200000
1.7 | 1 | Vendor Delays | delay implementing correctors / splitter - combiners | 2 | 3 | 6 | 2.4495 | 3.2361 | Early procurement / prioritize orders |  | 7 | 20000 | 3 months |  | 8000
1.7 | 2 | Ripple is too high | emittance growth | 2 | 3 | 6 | 2.4495 | 3.2361 |  | Provide external filtering for power supplies | 7 | 300000 | 12 months | After 4-turn test | 120000
1.8 | 1 | Availability of Controls Staff | Delays | 4 | 1 | 4 | 2 | 4 | identification of additional resources (Peter Q, Colwyn, CHESS, Adam B., Harsha P.) |  | 8 | 25000 | 3 months | After 4-turn test | 20000
1.8 | 2 | Timely definition of Controls requirements | Last minute controls development | 4 | 2 | 8 | 2.8284 | 4.1623 | Clear baseline requirements / design requirements |  | 8 | 25000 | 3 months | After 4-turn test | 20000
1.8 | 3 | Machine protection system cost higher than estimated (Feb 2017) | Higher costs | 3 | 2 | 6 | 2.4495 | 3.2361 | Prepare a solid engineering design for the system |  |  | 200000 | 6 months | about March 2018 | 120000
1.9 | 1 | BPM Performance inadequate / sensitivity insufficient | major impact on commissioning / operations | 3 | 3 | 9 | 3 | 3.8284 | Planned early stage BPM testing for verification of design |  | 9 | 300000 | 6 months | After 4-turn test | 180000
1.9 | 2 | Inadequate distribution of diagnostics tools around ring | delays to comissioning to shift resources | 3 | 2 | 6 | 2.4495 | 3.2361 | move dianostics as needed |  | 9 | 100000 | 3 months |  | 60000
1.9 | 3 | Loss monitor system cost higher than estimated (Feb 2017) | Higher costs | 3 | 2 | 6 | 2.4495 | 3.2361 | Prepare a solid engineering design for the system |  |  | 250000 | 6 months | about March 2018 | 150000
1.10 | 1 | Cannot achieve required level of vacuum | High beam loss due to residual gas scattering | 1 | 1 | 1 | 1 | 1 | Adding more pumping at instrumentation port, or/and explore in-situ mild bakeout |  | 10 | 30000 | 3 months | After final assembly and pre-beam commissioning complete (Milestone 8) | 6000
1.10 | 2 | Pumpdown time too long | Longer recovery time after a vacuum intervention, preventing accelertor on-schedule turn-on | 1 | 1 | 1 | 1 | 1 | Ensure to have adequte dry nitrogen purging during vent, or/and explore in-situ mild bakeout |  | 10 | 30000 | 3 months |  | 6000
1.10 | 3 | Beampipe interference to magnets | Preventing precision posititoning magnets to the required position | 2 | 3 | 6 | 2.4495 | 3.2361 | 1. Develop proper welding/assembling procedure to minimize beampipe distortion. 2. Locally reduce beampipe wall thickness without significantly impact beampipe mechanical property. |  | 10 | 100000 | 6 months | After final assembly and pre-beam commissioning complete (Milestone 8) | 40000
1.10 | 4 | Exceeding wake-field budgets | 1. Affect electron beam parameters; 2. Component over-heating. | 1 | 2 | 2 | 1.4142 | 2 | Identify potential high impedance vacuum components, and evaluate wakefield properties via simulation. Revise design as needed. | This will only have impact during high current operation, thus has no impact for achieving KPPs | 10 |  |  | N/A | 0
1.10 | 5 | BPM does not provide sufficient sensitivity or precision | Preventing required beam position measurement | 3 | 4 | 12 | 3.4641 | 4.6056 | 1. Test BPM design in early partial operations (such as beam through MLC, or/and partial-arc beam test) | Longer commissioning time required, system enhancements may be required. | 10 | 300000 | 6 months | After 4-turn test | 180000
1.11.1.6 | 1 | L0-RF system unable to power east cavities | Delay Partial Arc Test | 3 | 4 | 12 | 3.4641 | 4.6056 | Purchase new equipment. Potential cost +$100k |  | 11 | 300000 | 9 months | After MLC test | 180000
1.11.17 | 2 | L0 Pit RF Transmitter unable to properly operate | Delay Partial Arc Test | 3 | 3 | 9 | 3 | 3.8284 | Purchase new equipment. Potential cost +$100k |  | 11 | 300000 | 9 months | After MLC test | 180000
1.11.3 | 3 | CESR-85F water pumps create excessive vibration | Prevent intended operations | 2 | 2 | 4 | 2 | 2.4142 | Install antivibration components, or move pumps |  | 11 | 100000 | 3 months | Risk reduced after one-turn test. Can fully retire after 4-turn test. | 40000
1.11.6 | 4 | Water cooling capacity inadequate | Prevent intended operations | 2 | 3 | 6 | 2.4495 | 3.2361 | Additional cost to improve performance |  | 11 | 75000 | 3 months | After 1-turn test | 30000
1.11.8 | 5 | East wall modifications are more extensive than planned | Delay Partial Arc Test | 4 | 4 | 16 | 4 | 5.2426 | Additional cost to meet design requirements |  | 11 | 300000 | 6 months | After completion of partial arc test beam-line installation. | 240000
1.11.13 | 6 | HVAC unable to provide sufficient temperature and humidity | Prevent intended operations | 3 | 3 | 9 | 3 | 3.8284 | Additional cost to improve performance |  | 11 | 50000 | 3 months |  | 30000
1.12 | 1 | Construction schedule delays lead to limited commissioning time | ever limited time for comissioning. | 4 | 3 | 12 | 3.4641 | 4.6056 | multiple shifts, identifying additional BNL / CU expert operators => need for early training of experts during early BPM / MLC / FAT tests. |  | 12 | 60000 | 6 months | After final assembly and pre-beam commissioning complete (Milestone 8) | 48000
1.12 | 2 | lack of flexible commissioning plan. | ever limited time for comissioning. | 3 | 3 | 9 | 3 | 3.8284 | careful planning of commissioning and lots of time and staff allocated to commissioning |  | 12 | 60000 | 6 months | After 4-turn test | 36000
1.12 | 3 | High current operations lead to machine problems (near end of project with limited time) | machine damage (e.g. dump failure) | 2 | 2 | 4 | 2 | 2.4142 |  | High current not required for this project | 12 |  |  | N/A | 0
1.12 | 4 | Inadequate MPS leads to dump or beampipe failure | Severe | 2 | 5 | 10 | 3.1623 | 5.1231 |  |  | 12 | 1000000 | 6-12 months or more | At project completion | 400000
1.13 | 1 | Shielding requirements are greater than calculated / expected. | limits operation current / capabilites, $$ cost of replacement shielding | 3 | 3 | 9 | 3 | 3.8284 | careful calcs / conservative thickness. | many goals do not require high current. | 13 | 300000 | 6 months | After 1-turn test | 180000
1.13 | 2 | Personnel limitation for system development (few key people) | schedule slip / overruns | 4 | 2 | 8 | 2.8284 | 4.1623 |  | most systems are similar to existing safety systems | 13 | 150000 | 6 months | After final assembly and pre-beam commissioning complete (Milestone 8) | 120000
1.13 | 3 | Working around Permanent Magnets / damage to PM | Damage to magnet (?) / always on… careful policies for handling tools and equipment | 1 | 2 | 2 | 1.4142 | 2 | Spare magnets available / appropriate tools (Ti / BeCu) |  | 13 | 50000 | 6 months | At project completion | 10000
1.13 | 4 | Working around Permanent Magnets / minor accidents | always on… careful policies for handling tools and equipment | 2 | 4 | 8 | 2.8284 | 4.1623 | Good work planning |  | 13 | 100000 | 12 months | At project completion | 40000
1.13 | 5 | An unforeseen accident shuts down the lab / project until resolved. |  | 1 | 5 | 5 | 2.2361 | 5 | Good work planning |  | 13 | 100000 | 12 months | At project completion | 20000